## Project Settings
/Proyecto/PSP Fundamentals & Advanced/Program 3
PSP2 Project Plan Summary
Project Settings
Project Owner | Kevin Ray Marzola Otero
Start Date | mar 06, 2017 01:09:56 AM
Completion Date | mar 07, 2017 05:41:38 AM | Completed: *
Keywords
Language | Java
Adapted from "PSP Materials," copyright © 2006 Carnegie Mellon University. Used by permission.
Reporte generado a las 10:27 PM el 7/03/2017

## Overall Metrics
/Proyecto/PSP Fundamentals & Advanced/Program 3
PSP2 Project Plan Summary
Overall Metrics
Summary | Plan | Actual | A la Fecha
Size/Hour | 24.2 | 76.6 | 42.3
Planned Time | 0.31736 |  | 1899-12-31 00:37
Actual Tiempo |  | 0.29583 | 0.85625
CPI (Cost-Performance Index) |  |  | 1.2
% Reuse | 2.67% | 1.46% | 9.08%
% New Reusable | 0% | 0% | 0%
Test Defects/KLOC or equivalent | 12.3 | 0 | 4.6
Total Defects/KLOC or equivalent | 24.6 | 9.19 | 15
Yield % | 100% | 100% | 100%
Code Review Rate | #DIV/0! | 441 | 705
Adapted from "PSP Materials," copyright © 2006 Carnegie Mellon University. Used by permission.
Reporte generado a las 10:29 PM el 7/03/2017

## Program Size
/Proyecto/PSP Fundamentals & Advanced/Program 3
PSP2 Project Plan Summary
Program Size
| Plan | Actual | A la Fecha
Base (B) | 76 | 72 | 172
Deleted (D) | 5 | 10 | 55
Modified (M) | 0 | 0 | 25
Added (A) | 184 | 544 | 844
Reused (R) | 7 | 9 | 74
Added and Modified (A+M) | 184 | 544 | 869
Total Size (T) | 262 | 615 | 815
Total New Reusable | 0 | 0 | 0
Estimated Proxy Size (E) | 184 | 165 | 576
Adapted from "PSP Materials," copyright © 2006 Carnegie Mellon University. Used by permission.
Reporte generado a las 10:30 PM el 7/03/2017

## Time In Phase
/Proyecto/PSP Fundamentals & Advanced/Program 3
PSP2 Project Plan Summary
Time In Phase
| Plan | Actual | A la Fecha | % A la Fecha
PlaneaciÃ³n | 0.061806 | 0.061111 | 0.17083 | 20%
DiseÃ±o | 0.047917 | 0.00625 | 0.090972 | 10.6%
RevisiÃ³n de DiseÃ±o | 0 | 0.055556 | 0.055556 | 6.49%
CodificaciÃ³n | 0.1625 | 0.042361 | 0.32986 | 38.5%
RevisiÃ³n de CodificaciÃ³n | 0 | 0.051389 | 0.051389 | 6%
CompilaciÃ³n | 0.0069444 | 0.018056 | 0.029861 | 3.49%
Pruebas | 0.015278 | 0.015278 | 0.043056 | 5.03%
Postmortem | 0.022222 | 0.045833 | 0.084722 | 9.89%
Total | 0.31736 | 0.29583 | 0.85625
Adapted from "PSP Materials," copyright © 2006 Carnegie Mellon University. Used by permission.
Reporte generado a las 10:32 PM el 7/03/2017

## Defects Injected
/Proyecto/PSP Fundamentals & Advanced/Program 3
PSP2 Project Plan Summary
Defects Injected
| Plan | Actual | A la Fecha | % A la Fecha
Antes de Desarrollo | 0 | 0 | 0 | 0%
PlaneaciÃ³n | 0.57 | 1 | 2 | 15.4%
DiseÃ±o | 1.7 | 3 | 6 | 46.2%
RevisiÃ³n de DiseÃ±o | 0 | 0 | 0 | 0%
CodificaciÃ³n | 0 | 1 | 1 | 7.69%
RevisiÃ³n de CodificaciÃ³n | 0 | 0 | 0 | 0%
CompilaciÃ³n | 0 | 0 | 0 | 0%
Pruebas | 2.26 | 0 | 4 | 30.8%
Total | 4.53 | 5 | 13
Adapted from "PSP Materials," copyright © 2006 Carnegie Mellon University. Used by permission.
Reporte generado a las 10:33 PM el 7/03/2017

## Defects Removed
/Proyecto/PSP Fundamentals & Advanced/Program 3
PSP2 Project Plan Summary
Defects Removed
| Plan | Actual | A la Fecha | % A la Fecha
PlaneaciÃ³n | 0.57 | 1 | 2 | 15.4%
DiseÃ±o | 0.57 | 0 | 1 | 7.69%
RevisiÃ³n de DiseÃ±o | 0 | 2 | 2 | 15.4%
CodificaciÃ³n | 1.13 | 1 | 3 | 23.1%
RevisiÃ³n de CodificaciÃ³n | 0 | 1 | 1 | 7.69%
CompilaciÃ³n | 0 | 0 | 0 | 0%
Pruebas | 2.26 | 0 | 4 | 30.8%
Total | 4.53 | 5 | 13
After Development | 0 | 0 | 0
Adapted from "PSP Materials," copyright © 2006 Carnegie Mellon University. Used by permission.
Reporte generado a las 10:33 PM el 7/03/2017

## Defect Removal Efficiency
/Proyecto/PSP Fundamentals & Advanced/Program 3
PSP2 Project Plan Summary
Defect Removal Efficiency
| Plan | Actual | A la Fecha
Defects/Hour - Design Review | #DIV/0! | 1.5 | 1.5
Defects/Hour - Code Review | #DIV/0! | 0.81 | 0.81
Defects/Hour - Compile | 0 | 0 | 0
Defects/Hour - Test | 6.1 | 0 | 3.87
DRL (DLDR/UT) | #DIV/0! | 0.39 | 0.39
DRL (Code Review/UT) | #DIV/0! | 0.21 | 0.21
DRL (Compile/UT) | 0 | 0 | 0
Adapted from "PSP Materials," copyright © 2006 Carnegie Mellon University. Used by permission.
Reporte generado a las 10:34 PM el 7/03/2017